OBUASI EAST MUNICIPAL ASSEMBLY

(TUTUKA)

2026 MUNICIPAL COMPOSITE ANNUAL ACTION PLAN AND BUDGET

PREPARED BY:

MUNICIPAL PLANNING CO-ORDINATING UNIT (MPCU)

AUGUST, 2025

OBUASI EAST MUNICIPAL ASSEMBLY, TUTUKA

DRAFT 2026 MUNICIPAL COMPOSITE ANNUAL ACTION PLAN AND BUDGET

| ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To increase the contribution of IGF from 72.69% to 100% by 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Revenue Improvement Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S/N | Projects | Location | Time Frame |  |  |  | Cost |  |  |  | Programme Status |  | Implementing Institution/ Department |  |
|  |  |  | 1ST qrt | 2ND qrt | 3RD qrt | 4TH qrt | GoG GH₵ | DACF GH₵ | IGF GH₵ | DACF-RFG GH₵ | New | On-going | Lead | Colla- Borating |
| 1 | Valuation of properties in additional communities/areas and computerization of property rates data | Municipal wide |  |  |  |  |  | 30,000.00 |  |  |  |  | Finance | Cent. Admin |
| 2 | Organise 2No. Social Accountability Forum (Town Hall Meetings) | Tutuka |  |  |  |  |  | 60,000.00 |  |  |  |  | Cent. Admin | Finance |
| 3 | Enforce Municipal Assembly by-laws by prosecuting recalcitrant defaulters | Municipal wide |  |  |  |  |  |  | 10,000.00 |  |  |  | Cent. Admin | Finance |
| 4 | Effective supervision of Revenue Task Force and assign roles for efficient revenue collection | Municipal wide |  |  |  |  |  |  | 10,000.00 |  |  |  | Cent. Admin | Finance |
| 5 | Undertake municipal wide Data Collection Exercise on all data/revenue items and development of Revenue Data Software | Municipal wide |  |  |  |  |  | 30,000.00 | 15,000.00 |  |  |  | Statistics Dept. | Finance, Cent. Admin |
| 6 | Construction and Operationalisation of 24hr Economy Market (NEW PROJECT) | Boete |  |  |  |  |  | 7,804,544.83 |  |  |  |  | Works Dept. | Cent. Admin. |
| 7 | Completion of Community Initiated Market (NEW PROJECT) | Ahansonyewodea |  |  |  |  |  | 300,000.00 |  |  |  |  | Works Dept. | Cent. Admin. |
|  | PRIVATE SECTOR DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective: To provide jobs for 5000 unemployed Youth by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Youth Employment Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Youth Apprenticeship Programme (YAP) | Municipal wide |  |  |  |  |  | 25,000.00 |  |  |  |  | Trade & Industry BRC | Cent. Admin. |
| 9 | Organise skills training for Local Artisans | Municipal wide |  |  |  |  |  | 15,000.00 |  |  |  |  | Trade & Industry BRC | Cent. Admin. |
| 10 | NVTI Certificate Examination | Municipal wide |  |  |  |  |  | 20,000.00 |  |  |  |  | Trade & Industry BRC | Cent. Admin. |
| 11 | Training in Occupational Safety Health and Environmental Management and Quality improvement for local artisans. | Municipal wide |  |  |  |  |  | 10,500.00 |  |  |  |  | Trade & Industry BRC | Cent. Admin. |
| 12 | Support to Local Economic Development (LED) through technical skills training in Products Packaging, branding, Labelling and cassava Processing | Municipal wide |  |  |  |  |  | 20,000.00 |  |  |  |  | Trade & Industry BRC | Cent. Admin. |
| 13 | Community Based Training in Soap and Detergent Making, Beads Making, Baking, wigs fixing, eye las, makeups etc | Municipal wide |  |  |  |  |  | 35,000.00 |  |  |  |  | Trade & Industry BRC | Cent. Admin. |
| 14 | Maintenance of Cassava processing machine (NEW PROJECT) | Mampamhwe |  |  |  |  |  | 30,000.00 |  |  |  |  | Works Dept. | Cent. Admin. |
| 15 | Development of Obuasi Business Park (NEW PROJECT) | PTP/ETS |  |  |  |  | PPP | PPP | PPP | PPP | PPP | PPP | PPP | PPP |
| 16 | Construction of KNUST Obuasi Hotels for Students (NEW PROJECT) | PTP |  |  |  |  | PPP | PPP | PPP | PPP | PPP | PPP | PPP | PPP |
| Objective: To support 50 MSEs to improve productivity and quality of their products by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Youth Employment Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 | Orgainse 2No. Micro and Small-Scale Enterprise Business Forum/MSE Stakeholders Meeting | Wawase |  |  |  |  |  | 10,000.00 |  |  |  |  | Trade & Industry BRC | Cent. Admin. |
| Objective: To develop 2 tourist sites in the municipality by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Tourism Development Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 | Support the Development of Tourism and Culture | Municipal wide |  |  |  |  |  | 20,000.00 |  |  |  |  | Cent. Admin. | Trade & Industry BAC |
| 19 | Support to Obuasi Trade Show | Obuasi |  |  |  |  |  | 20,000.00 |  |  |  |  | Trade & Industry BRC | Cent. Admin. |
|  | AGRICULTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective: To improve upon agriculture productivity by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Agriculture Modernization Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20 | Maintenance and Repair of Vehicle, Motorbikes and Fuel.(Administrative Support to Agric Directorate) | Municipal wide |  |  |  |  |  | 50,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 21 | Organize educational forum for farmers on FEED GHANA PROGRAMME, PERD and LED and also supply farmers with improved cassava and oil palm planting materials | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 22 | Educate and Vaccinate 500 pets (dogs and cats) and 500 small ruminants against rabies and PPR | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 23 | Educate 80 Farmers on Climate Change and Climate Smart Agriculture | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 24 | Organise and celebrate Municipal Farmers Day | Selected Community |  |  |  |  |  | 150,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 25 | Home and Farm Visits by AEAs to educate farmers on improved crops and livestock technologies | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 26 | 960 Monitoring and backstopping activities by MAOs | Municipal wide |  |  |  |  |  | 15,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 27 | Introduce and demonstrate climate smart crop varieties | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 28 | Train FBOs on groups dynamics, record keeping, book keeping as alternative livelihood project | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 29 | Organize RELC Planning Session | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 30 | Organise training for livestock farmers on good breeding stock and husbandry practices | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
|  | Objective: To reduce post-harvest losses from 40% to 5% by the year 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Agriculture Modernization Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31 | Organize 4 Post Harvest forums for 100 farmers on Post Harvest management of cereals, legumes, vegetables, root and tubers in farming communities | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 32 | Train Gari processors (women) on Food fortification using Soybean and gari and also the preparation of yoghurt | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 33 | Train and sensitize 30 Women processors on Value addition, standardization, food safety hygiene at processing sites packaging, branding and marketing | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 34 | Organise 2 trainings for 40 women and PWDs on Mushroom production and preservation | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| 35 | Organise training on the storage and processing of cereals and legumes for women and PWD | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | Agric Dept. | Cent. Admin. |
| SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective: To provide 16No. KG, 16No. Primary and 16No. JHS school blocks and Teaching Learning Materials by the end of 2029. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Educational Improvement Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 36 | Construction of 1No. 2 storey 6-unit classroom block with 15-seater water closet toilet, 4-columns water concrete stand and 2No. Rambo 400 poly tank (ON-GOING PROJECT ROLL OVER TO 2026) | Low Cost |  |  |  |  |  | 1,663,488.50 |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 37 | Construction and Completion of 1No. 6 Unit first Floor of an existing classroom block (COMPLETED PENDING OUTSTANDING PAYMENT) | Boete |  |  |  |  |  |  | 99,542.82 IGF |  |  |  | Works Dept. | Cent. Admin. GES |
| 38 | Construction of 1No. 6-unit classroom block (ON-GOING PROJECT ROLL OVER TO 2026) | Domeabra |  |  |  |  | 1,424,041.80 (GET fund) Outstanding Payment |  |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 39 | Construction of 1No. 6-unit classroom block (ON-GOING PROJECT ROLL OVER TO 2026) | Pomposo |  |  |  |  | 1,424,041.80 (GET fund) Outstanding Payment |  |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 40 | Construction of 1No. 3-unit classroom block with office, store and staff common room and 5-seater W/C Toilet facility for primary school (NEW PROJECT) | Kwabenakwa |  |  |  |  |  | 950,000.00 DACF |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 41 | Construction of 1No. 2-unit Classroom Block with office, store and 4-seater W/C Toilet and 1No. mechanized Borehole with concrete water stand and 500liters Poly Tank (IN PROCUREMENT PROCESS FOR AWARD OF CONTRACT)) | Nyamesomyede |  |  |  |  |  | 746,754.00 DACF |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 42 | Construction of 1No. 2-unit Classroom Block with office, store and 4-seater W/C Toilet and 1No. mechanized Borehole with concrete water stand and 500liters Poly Tank (NEW PROJECT) | Tutuka Sampsonkrom |  |  |  |  |  | 750,000.00 DACF |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 43 | Construction of 1No. 6-unit classroom Block with Office, store and staff common room and 12-seater W/C Toilet facility with mechanized borehole (NEW PROJECT) | Asonkore |  |  |  |  |  | 1,600,000.00 DACF |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 44 | Construction of 1No. 3-unit classroom Block with Office, store and staff common room and 5-seater W/C Toilet facility (NEW PROJECT) | Nyamesomyede |  |  |  |  |  | 950,000.00 DACF |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 45 | Construction of 1No. 6-unit classroom Block with Office, store and staff common room and 12-seater W/C Toilet facility with mechanized borehole (NEW PROJECT) | Odumasi |  |  |  |  |  |  |  | 1,600,000.00 DACF-RFG |  |  | Works Dept. | Cent. Admin. GES |
| 46 | Renovation of Dilapidated Classroom blocks (NEW PROJECT) | Selected schools |  |  |  |  |  | 1,000,000.00 DACF |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 47 | Construction of Semi-detached Teachers Quarters (NEW PROJECT) | Jimiso |  |  |  |  |  |  |  | DACF-RFG |  |  | Works Dept. | Cent. Admin. GES |
| 48 | Construction and Furnishing of 1No. 3-unit science laboratory block with office, store and staff common room and 5-seater W/C Toilet facility for CKC SHS (NEW PROJECT) | CKC SHS Akaporiso |  |  |  |  |  |  |  | 950,000.00 DACF-RFG |  |  | Works Dept. | Cent. Admin. GES |
| 49 | Conversion of Community Day School to Nursing and Midwifery Training College (NEW PROJECT) | Kwabenakwa |  |  |  |  |  | Central Govt | Central Govt | Central Govt |  |  | Cent. Admin. | GES, Works Dept |
| 50 | Construction of Community Football Pitch with Chain link fence and a mechanized borehole (ON-GOING PROJECT ROLL OVER TO 2026) | Odumasi |  |  |  |  |  | 413,096.50 MPCF |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 51 | Construction of Community Football Pitch with mechanized borehole (ON-GOING PROJECT ROLL OVER TO 2026) | Kwabenakwa |  |  |  |  |  | 306,505.00 MPCF |  |  |  |  | Works Dept. | Cent. Admin. GES |
| 52 | Supply of School Furniture (round set tables and chairs, mono and dual desk) and Teachers Table and Chairs (NEW PROJECT) | All Basic Schools |  |  |  |  |  | 3,121,817.93 |  |  |  |  | Cent. Admin. | GES |
| 53 | Procure 20No. Desktop Computers and Accessories for Municipal Library and basic schools (NEW PROJECT) | All Basic Schools |  |  |  |  |  | 250,000.00 |  |  |  |  | Cent. Admin. | GES |
| 54 | Organise orientation for BECE Candidates | All Basic Schools |  |  |  |  |  | 30,000.00 |  |  |  |  | GES | Cent. Admin. |
| 55 | Organize termly capacity building for Head teachers and class teachers to sharpen their skills | All Basic Schools |  |  |  |  |  | 40,000.00 |  |  |  |  | GES | Cent. Admin. |
| 56 | Support to STME Development | All Basic Schools |  |  |  |  |  | 40,000.00 |  |  |  |  | GES | Cent. Admin. |
| 57 | Support to Sports Development | All Basic Schools |  |  |  |  |  | 30,000.00 |  |  |  |  | GES | Cent. Admin. |
| 58 | Sensitization Programme on Girl Child Education | All Basic Schools |  |  |  |  |  |  | 10,000.00 |  |  |  | GES | Cent. Admin. |
| 59 | Organise counselling programmes for all stakeholders in schools on climate and positive personal Relationships | All Basic Schools |  |  |  |  |  |  | 5,000.00 |  |  |  | GES | Cent. Admin. |
| 60 | Support to needy but brilliant students | All Basic Schools |  |  |  |  |  | 300,000.00 |  |  |  |  | GES | Cent. Admin. |
| 61 | Support to best teacher awards | Municipal wide |  |  |  |  |  | 50,000.00 |  |  |  |  | GES | Cent. Admin. |
| 62 | Administrative Support to Municipal Education Directorate | Boete |  |  |  |  |  | 50,000.00 |  |  |  |  | GES | Cent. Admin. |
|  | HEALTH |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective: To construct to 8No. CHPS Compound and Municipal Hospital with nurses quarters and mechanized borehole by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Health Improvement Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 63 | Construction of 1No. CHPS Compound with 5No. Lavatories and 2No. bedroom semi-detached Nurses Quarters and Mechanised Borehole with concrete water stand and 2No. 500liters Poly Tank (IN PROCUREMENT PROCESS FOR AWARD OF CONTRACT) | Ayease |  |  |  |  |  | 1,600,000.00 DACF |  |  |  |  | Works Dept. | Cent. Admin. GHS |
| 64 | Construction of 1No. CHPS Compound with 5No. Lavatories and 2No. bedroom semi-detached Nurses Quarters and Mechanised Borehole with concrete water stand and 2No. 500liters Poly Tank (NEW PROJECT) | Domeabra |  |  |  |  |  | 1,600,000.00 DACF |  |  |  |  | Works Dept. | Cent. Admin. GHS |
| 65 | Construction of 1No. CHPS Compound with 5No. Lavatories and 2No. bedroom semi-detached Nurses Quarters and Mechanised Borehole with concrete water stand and 2No. 500liters Poly Tank (NEW PROJECT) | Jimiso |  |  |  |  |  | 1,600,000.00 DACF |  |  |  |  | Works Dept. | Cent. Admin. GHS |
| 66 | Construction of 1No. CHPS Compound with 5No. Lavatories and 2No. bedroom semi-detached Nurses Quarters and Mechanised Borehole with concrete water stand and 2No. 500liters Poly Tank (NEW PROJECT) | Bossman |  |  |  |  |  | 1,600,000.00 DACF |  |  |  |  | Works Dept. | Cent. Admin. GHS |
| 67 | Construction of 1No. Medical Laboratory with 1No. office and 2-seater W/C toilet for Odumasi Health Center (ON-GOING PROJECT ROLL OVER TO 2026) | Odumasi Health Center |  |  |  |  |  |  | 314,985.55 IGF |  |  |  | Works Dept. | Cent. Admin. GHS |
| 68 | Construction of 1No. CHPS Compound with 5No. Lavatories and Urinal and a 2No. bedroom semi-detached Nurses Quarters and a Mechanised Borehole with 2No. 500liters Poly Tank with Pipe Stand and Tank Stand (ON-GOING PROJECT ROLL OVER TO 2026) | Kwameduakrom |  |  |  |  | 285,887.56 (MDF) Outstanding Payment |  |  |  |  |  | Works Dept. | Cent. Admin. GHS |
| 69 | Construction of 1No. CHPS Compound with 5No. Lavatories and Urinal and a 2No. bedroom semi-detached Nurses Quarters and a Mechanised Borehole with 2No. 500liters Poly Tank with Pipe Stand and Tank Stand (ON-GOING PROJECT ROLL OVER TO 2026) | Anyimadukrom |  |  |  |  | 352,778.74 (MDF) Outstanding Payment |  |  |  |  |  | Works Dept. | Cent. Admin. GHS |
| 70 | Intensify health education on the danger signs in pregnancy and sensitize pregnant women to report to the health facility early. | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | GHS | Cent. Admin. |
| 71 | Intensify health education on nutrition for pregnant women | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | GHS | Cent. Admin. |
| 72 | Health education in all aspect of maternal care. | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | GHS | Cent. Admin. |
| 73 | Education on suspected cases of Polio, Measles, Yellow Fever etc. in the communities | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | GHS | Cent. Admin. |
| 74 | Train 20 midwives and 30 CHOs in long term family planning methods | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | GHS | Cent. Admin. |
| 75 | Administrative Support to the Municipal Health Directorate | Municipal wide |  |  |  |  |  | 50,000.00 |  |  |  |  | GHS | Cent. Admin. |
| 76 | Monitoring and supervision on Malaria (0.5%) activities | Municipal wide |  |  |  |  |  |  |  |  |  |  | GHS | Cent. Admin. |
| Objective: To ensure the reduction of new HIV and AIDS/STIs infections, especially among the vulnerable groups by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: HIV Counselling and Testing Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 77 | Support to municipal response initiative on HIV and AIDS | Municipal wide |  |  |  |  |  | 155,000.00 |  |  |  |  | GHS | Cent. Admin. |
| 78 | Support to immunization programmes in the municipality | Municipal wide |  |  |  |  |  | 20,000.00 |  |  |  |  | GHS | Cent. Admin. |
|  | SOCIAL PROTECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective: To increase awareness on the effects of child labour and child protection abuses by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Social Protection Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 79 | Undertake child protection education in schools and communities | Municipal wide |  |  |  |  | 4,000.00 | 4,000.00 | 4,000.00 |  |  |  | DSW/CD | Cent. Admin. |
| 80 | Conduct quarterly inspection of day care centres | Municipal wide |  |  |  |  | 1,000.00 | 3,000.00 | 3,000.00 |  |  |  | DSW/CD | Cent. Admin. |
| 81 | Assist families to resolve child and family welfare issues | Municipal wide |  |  |  |  | 3,000.00 |  |  |  |  |  | DSW/CD | Cent. Admin. |
| 82 | Organise a stakeholder meeting on Child Protection and Family Welfare | Municipal Assembly |  |  |  |  | 6,600.00 |  |  |  |  |  | DSW/CD | Cent. Admin. |
| 83 | Organise Municipal Child Protect Committee meetings | Municipal Assembly |  |  |  |  | 4,000.00 | 4,000.00 | 4,000.00 |  |  |  | DSW/CD | Cent. Admin. |
| 84 | Organise training for Community Child Protection Committees in 25 communities | 25 Communities |  |  |  |  | 27,000.00 |  |  |  |  |  | DSW/CD | Cent. Admin. |
| 85 | Organize the Observation of World Day Against Child Labour | Selected community |  |  |  |  |  | 20,000.00 | 3,000.00 |  |  |  | DSW/CD | Cent. Admin. |
| 86 | Support the LEAP programme implementation | All LEAP communities |  |  |  |  | 3,000.00 |  | 3,000.00 |  |  |  | DSW/CD | Cent. Admin. |
| 87 | Assist indigents and persons with disability for free health insurance registration/renewal | Municipal wide |  |  |  |  |  |  | 1,000.00 |  |  |  | DSW/CD | Cent. Admin. |
| 88 | Register and sensitize persons with disability (PWD) in the municipality | Municipal wide |  |  |  |  |  | 20,000.00 |  |  |  |  | DSW/CD | Cent. Admin. |
| 89 | Organise skills training for PWDs | Wawase |  |  |  |  |  | 80,000.00 |  |  |  |  | DSW/CD | Cent. Admin. |
| 90 | Support PWDs organizational activities | Municipal wide |  |  |  |  |  | 40,000.00 |  |  |  |  | DSW/CD | Cent. Admin. |
| 91 | Provide monitoring and administrative support to disability activities | Municipal wide |  |  |  |  |  | 40,000.00 | 5,000.00 |  |  |  | DSW/CD | Cent. Admin. |
| 92 | Support PWDs in education and vocational training | Municipal wide |  |  |  |  |  | 40,000.00 |  |  |  |  | DSW/CD | Cent. Admin. |
| 93 | Support PWDs in economic activities with equipment, logistics and facilities. | Municipal wide |  |  |  |  |  | 580,000.00 |  |  |  |  | DSW/CD | Cent. Admin. |
| 94 | Support PWDs with medical and assistive devices. | Municipal wide |  |  |  |  |  | 40,000.00 |  |  |  |  | DSW/CD | Cent. Admin. |
| 95 | Register Non-Profit Organisations (NPOs) operating in the municipality | Municipal wide |  |  |  |  |  |  | 3,000.00 |  |  |  | DSW/CD | Cent. Admin. |
| 96 | Support the destitute and paupers, including hospital welfare | Municipal wide |  |  |  |  | 4,000.00 |  | 4,000.00 |  |  |  | DSW/CD | Cent. Admin. |
| 97 | Acquire 1 motorbike, 1 laptop, materials and stationery for the Department | DSW/CD |  |  |  |  | 1,000.00 | 40,000.00 | 3,000.00 |  |  |  | DSW/CD | Cent. Admin. |
| 98 | Sensitization on domestic and gender-based violence and child marriage | Municipal wide |  |  |  |  | 4,000.00 | 10,000.00 |  |  |  |  | DSW/CD | Cent. Admin. |
| 99 | Organize capacity building programmes on gender mainstreaming | Municipal wide |  |  |  |  |  | 15,000.00 |  |  |  |  | DSW/CD | Cent. Admin. |
| 100 | Equip women with entrepreneurial skills and link them with start-up capital | Municipal wide |  |  |  |  |  | 20,000.00 |  |  |  |  | DSW/CD | Cent. Admin. |
| 101 | Celebration of Disability Day | Wawase |  |  |  |  |  | 30,000.00 |  |  |  |  | DSW/CD | Cent. Admin. |
| ENVIRONMENT AND HUMAN SETTLEMENTS DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ROADS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Objective: To ensure 35km of feeder roads are accessible by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Road Improvement Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 102 | Extension of alternative access road from Tutuka-Tiatiaso to Boete through the construction of 2M X 2M Double Box Culvert at Tiatiaso (ON-GOING PROJECT ROLL OVER TO 2026) | Tutuka-Tiatiaso to Boete |  |  |  |  |  | 540,000.00 |  |  |  |  | Roads Dept | Cent. Admin., Works Dept |
| 103 | Construction of 2M X 2M Double Box Culvert (IN PROCUREMENT PROCESS FOR AWARD OF CONTRACT) | Kwabrafoso |  |  |  |  |  | 540,000.00 |  |  |  |  | Roads Dept | Cent. Admin., Works Dept |
| 104 | Construction and Completion of 1No community center with 2No. rooms and 10- seater water closet toilet facility and mechansied borehole (ON-GOING PROJECT ROLL OVER TO 2026) | Akaporiso |  |  |  |  |  | 886,476.00 DACF |  |  |  |  | Works Dept | Cent. Admin. |
| 105 | Construction of 2meters x 1.2 meters storm water drains from Tutuka Methodist Church to Nkwadum (NEW PROJECT) | Tutuka Methodist Church to Nkwadum |  |  |  |  |  | 2,406,212.00 MPCF |  |  |  |  | Roads Dept | Cent. Admin. |
| 106 | Construction of Culverts and Storm drains (NEW PROJECT) | Asonkore Tutuka Bossman Kokoase Kwabenakwa Brahabebome Aboagyekrom |  |  |  |  |  | 1,500.000.00 DACF |  | 1,500.000.00 DACF-RFG |  |  | Roads Dept | Cent. Admin. Works Dept |
| 107 | Construction of 5No. footbridges over water course (NEW PROJECT) | Selected Communities |  |  |  |  |  | 600,000.00 |  |  |  |  | Works Dept | Cent. Admin. |
| 108 | Fuel support for reshaping of roads and Maintenance of DRIP Equipment | Municipal wide |  |  |  |  |  | 400,000.00 |  |  |  |  | Works Dept | Cent. Admin. |
| 109 | Sensitization of Commercial/Trotro Drivers on Road Safety interventions | Wawase |  |  |  |  |  | 10,000.00 |  |  |  |  | Transport Dept | Cent. Admin. |
| 110 | Embark on road routine maintenance such as spot improvement, pothole patching, road markings, zebra crossing and Traffic management | Municipal wide |  |  |  |  |  | 50,000.00 |  |  |  |  | Roads Dept | Cent. Admin. |
|  | WATER AND SANITATION |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Objective: To increase access to potable water by 20% by the end 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Water and Sanitation Improvement Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 111 | Drilling and Mechanisation of 17No. boreholes with concrete water stand and 500liters Poly Tank and repair and maintenance of 5No. damaged boreholes (IN PROCUREMENT PROCESS FOR AWARD OF CONTRACT) | Selected Communities |  |  |  |  |  | 1,725,408.84.00 |  |  |  |  | Works Dept | Cent. Admin. |
| 112 | Drilling and Mechanisation of 25No. boreholes with concrete water stand and 500liters Poly Tank and repair and maintenance of 10No. damaged boreholes (NEW PROJECT) | Selected Communities |  |  |  |  |  | 2,500,000.00 |  |  |  |  | Works Dept | Cent. Admin. |
|  | Objective: To increase access to improve sanitation by 35% by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Water and Sanitation Improvement Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 113 | Construction of 1No. 12-seater W/C toilet facility (ON-GOING PROJECT ROLL OVER TO 2026) | Domeabra Basic School |  |  |  |  | 440,981.85 (GETfund) Outstanding Payment |  |  |  |  |  | Works Dept | Cent. Admin. |
| 114 | Construction of 1No. 12-seater W/C toilet facility (ON-GOING PROJECT ROLL OVER TO 2026) | Pomposo Basic School |  |  |  |  | 440,981.85 (GETfund) Outstanding Payment |  |  |  |  |  | Works Dept | Cent. Admin. |
| 115 | Construction of Septic Tank for newly constructed Head Teacher’s office at Owusu Sampa JHS (NEW PROJECT) | Ahansonyewodea |  |  |  |  |  |  | 20,000.00 |  |  |  | Works Dept | Cent. Admin. |
| 116 | Support to Hygiene Education | Municipal wide |  |  |  |  |  |  | 10,000.00 |  |  |  | Cent. Admin. |  |
| 117 | Food Vendor Screening | Municipal wide |  |  |  |  |  |  | 5,000.00 |  |  |  | Cent. Admin. |  |
| 118 | Celebration of World Toilet Day | Municipal wide |  |  |  |  |  | 20,000.00 |  |  |  |  | Cent. Admin. |  |
| 119 | Intensify Premises Inspection | Municipal wide |  |  |  |  |  |  | 5,000.00 |  |  |  | Cent. Admin. |  |
| 120 | Fumigation of all sanitary sites and disinfection of public open places | Municipal wide |  |  |  |  |  | 370,000.00 |  |  |  |  | Cent. Admin. |  |
| 121 | Procure Sanitary cleaning equipment | Municipal wide |  |  |  |  |  | 100,000.00 |  |  |  |  | Cent. Admin. |  |
| 122 | Evacuation of Refuse and maintenance of final disposal site | All satellite refuse Dump and final refuse disposal site |  |  |  |  |  | 300,000.00 |  |  |  |  | Cent. Admin. |  |
| 123 | Sanitation Improvement Package | Municipal wide |  |  |  |  |  | 387,205.00 |  |  |  |  | Cent. Admin. |  |
| 124 | Procurement of 5No. Refuse containers | Municipal wide |  |  |  |  |  | 250,000.00 |  |  |  |  | Cent. Admin. |  |
| 125 | Support to Monthly National Sanitation Day | Municipal wide |  |  |  |  |  | 100,000.00 |  |  |  |  | Cent. Admin. |  |
| 126 | Procurement of 5 No. Tricycle | Municipal wide |  |  |  |  |  | 200,000.00 |  |  |  |  | Cent. Admin. |  |
| 127 | Procurement of 1 No. Cesspool emptier | Municipal wide |  |  |  |  |  | 906,920.00 |  |  |  |  | Cent. Admin. |  |
| 128 | Renovation of Slaughter House (NEW PROJECT) | Kwabenakwa |  |  |  |  |  | 250,000.00 |  |  |  |  | Works Dept | Cent. Admin. |
| 129 | Dredging and Desilting of streams and choked gutters | Municipal wide |  |  |  |  |  | 400,000.00 |  |  |  |  | Works Dept | Cent. Admin. |
| 130 | Development of new cemetery site (NEW PROJECT) | Asonkore |  |  |  |  |  |  | 50,000.00 |  |  |  | Works Dept | Cent. Admin. |
|  | Objective: To increase access to electricity by 5% by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Rural Electrification Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 131 | Procure 500No. low tension electricity poles for various communities and Extension of electricity to newly built-up areas | Municipal wide |  |  |  |  |  | 600,000.00 |  |  |  |  | Cent. Admin. | ECG Works Dept |
| 132 | Extension of electricity to some selected basic schools without light | Selected Schools |  |  |  |  |  | 20,000.00 |  |  |  |  | Works Dept | Cent. Admin. |
| 133 | Procure 500No. Led Street Light Bulbs with Photocell | Municipal wide |  |  |  |  |  | 500,000.00 |  |  |  |  | Cent. Admin. |  |
| 134 | Repairs and Maintenance of all Faulty Bulbs | Selected Communities |  |  |  |  |  | 10,000.00 |  |  |  |  | Works Dept | Cent. Admin. |
|  | SPATIAL PLANNING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Objective: To ensure all 32 communities have local and structure Plan to promote proper settlement planning by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Human Settlement Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 135 | Street Naming and Property Addressing Project. | Municipal wide |  |  |  |  |  | 150,000.00 |  |  |  |  | PPD | Works Dept. Cent. Admin. |
| 136 | Preparation of 3 Local Plans for selected communities | Asonkore North, Mampamhwe, Odumasi |  |  |  |  |  | 150,000.00 |  |  |  |  | PPD | Works Dept., Cent. Admin. |
| 137 | Undertake monthly joint site inspections on development | Municipal wide |  |  |  |  |  |  | 30,000.00 |  |  |  | PPD | Works Dept., Cent. Admin. |
| 138 | Embark on Monthly Technical and Spatial Planning Committee Meetings | Municipal wide |  |  |  |  |  |  | 100,000.00 |  |  |  | PPD | Works Dept. Cent. Admin. |
| 139 | Embark on Development Control | Municipal wide |  |  |  |  |  | 50,000.00 |  |  |  |  | PPD | Works Dept. Cent. Admin. |
| 140 | Organise Training for Local Artisans on Development Control and Permit Acquisition | Municipal wide |  |  |  |  |  | 20,000.00 |  |  |  |  | PPD | Works Dept., Cent. Admin. |
| 141 | Support to Community Initiated Projects/Self Help Projects | Municipal wide |  |  |  |  |  | 400,000.00 | 200,000.00 |  |  |  | Cent. Admin. | Works Dept. |
|  | Objective: To reduce the incidence of illegal mining by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Disaster Risk Reduction Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 142 | Tree for Life Reforestation Initiative | Municipal wide |  |  |  |  |  | 20,000.00 |  |  |  |  | NADMO | Cent. Admin., Forestry |
| 143 | Conduct public education on disaster risk reduction programmes (DRR) | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | NADMO, GNFS | Cent. Admin. |
| 144 | Celebration of World Disaster Day | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | NADMO, GNFS | Cent. Admin. |
| 145 | Support to Disaster Victims | Municipal wide |  |  |  |  |  | 20,000.00 |  |  |  |  | NADMO | Cent. Admin. |
| 146 | Training of Disaster Volunteer Groups (DVG’s) | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | NADMO, GNFS | Cent. Admin. |
| 147 | Undertake Field Trips on Hazard Assessment | Municipal wide |  |  |  |  |  | 10,000.00 |  |  |  |  | NADMO, GNFS | Cent. Admin. |
| 148 | Reclamation of all galamsey pits | Municipal wide |  |  |  |  |  |  | 50,000.00 |  |  |  | NADMO, | Cent. Admin. PPD |
| GOVERNANCE AND INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Objective: To improve the Capacity of Assembly Staff, Town Councils and Unit Committees by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Capacity Improvement Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 149 | Construction of 3No. Storey Office Administration Block for the District Assembly (ON-GOING PROJECT ROLL OVER TO 2026) | Pomposo |  |  |  |  | Central Gov. | Central Gov. | Central Gov. | Central Gov. |  |  | Central Gov. | Cent. Admin. |
| 150 | Construction and Furnishing of 2No. Police Station with lavatories and mechanized borehole (NEW PROJECT) | Boete and Odumasi |  |  |  |  |  |  |  | DACF-RFG |  |  | Works Dept | Cent. Admin. |
| 151 | Completion of MCE’s residential bungalow (ON-GOING PROJECT ROLL OVER TO 2026) | Pomposo |  |  |  |  | Central Gov. | Central Gov. | Central Gov. | Central Gov. |  |  | Central Gov. | Cent. Admin. |
| 152 | Rehabilitation of Official Residential Building | Municipal wide |  |  |  |  |  | 400,000.00 |  |  |  |  | Works Dept | Cent. Admin. |
| 153 | Procure Office equipment, computers and accessories | Obuasi East Municipal Assembly |  |  |  |  |  | 150,000.00 |  |  |  |  | Cent. Admin. |  |
| 154 | Procure printed materials and stationaries | Obuasi East Municipal Assembly |  |  |  |  |  | 50,000.00 |  |  |  |  | Cent. Admin. |  |
| 155 | Procure Office furniture, fixtures and fittings | Obuasi East Municipal Assembly |  |  |  |  |  | 150,000.00 |  |  |  |  | Cent. Admin. |  |
| 156 | Procure 1No. 3 Face Generator for New MA Administration Block at Pomposo | Obuasi East Municipal Assembly at Pomposo |  |  |  |  |  | 70,000.00 |  |  |  |  | Cent. Admin. | Works Dept |
| 157 | Procurement of 1No. Pick-up Vehicle (NEW PROJECT) | Obuasi East Municipal Assembly |  |  |  |  |  | 700,000.00 |  |  |  |  | Cent. Admin. |  |
| 158 | Training and development expenses | Obuasi East Municipal Assembly |  |  |  |  |  | 62,378.00 |  |  |  |  | HR | Cent. Admin. |
| 159 | Recruitment and hiring expenses | Obuasi East Municipal Assembly |  |  |  |  |  | 15,402.00 |  |  |  |  | HR | Cent. Admin. |
| 160 | Employee engagement and retention initiative | Obuasi East Municipal Assembly |  |  |  |  |  | 25,302.00 |  |  |  |  | HR | Cent. Admin. |
| 161 | Procure 2No. office table and chair for the HR | Obuasi East Municipal Assembly |  |  |  |  |  | 23,682.00 |  |  |  |  | HR | Cent. Admin. |
| 162 | Support to the celebration of national programmes (6th March etc.) | Municipal wide |  |  |  |  |  | 150,000.00 |  |  |  |  | Cent. Admin. |  |
| 163 | Maintenance of Municipal Assembly Official Vehicles | Municipal wide |  |  |  |  |  | 40,000.00 | 20,000.00 |  |  |  | Transp. Dept. | Cent. Admin. |
| 164 | Maintenance of Municipal Assembly Office buildings | PTP |  |  |  |  |  | 80,000.00 |  |  |  |  | Works Dept | Cent. Admin. |
| 165 | NALAG Dues | Municipal wide |  |  |  |  |  | 99,898.17 |  |  |  |  | Cent. Admin. |  |
| 166 | Workshops, Conference, Training and Seminars | Municipal wide |  |  |  |  |  | 50,000.00 | 200,000.00 |  |  |  | HR |  |
| 167 | Statutory and other Assembly Meetings | Municipal wide |  |  |  |  |  |  | 150,000.00 |  |  |  | Cent. Admin. |  |
| 168 | Funeral Donations, Weddings and other social programmes | Municipal wide |  |  |  |  |  |  | 50,000.00 |  |  |  | HR |  |
| 169 | Support to Internal Audit Unit and Audit Committee Meetings | Municipal wide |  |  |  |  |  |  | 50,000.00 |  |  |  | Cent. Admin. |  |
| 170 | Support to MCE Engagement with the Community | Municipal wide |  |  |  |  |  | 60,000.00 |  |  |  |  | Cent. Admin. |  |
| 171 | Preparation of 2027 Programme Based Budget and Annual Action Plan | Municipal wide |  |  |  |  |  | 70,000.00 |  |  |  |  | Cent. Admin. |  |
| 172 | Support to Municipal Wide Project Monitoring and Evaluation | Municipal wide |  |  |  |  |  | 80,000.00 |  |  |  |  | Cent. Admin. |  |
| 173 | Servicing of Computers and accessories | Municipal wide |  |  |  |  |  |  | 20,000.00 |  |  |  | Cent. Admin. |  |
| 174 | Public Education on birth and death registration | Municipal wide |  |  |  |  |  | 15,000.00 |  |  |  |  | Birth and Death Registry | NCCE, ISD |
| 175 | Support to 3No. Sub Structures | Wawase Kwabrafoso, Brahabebome Akoporiso, Tutuka Odumasi Town Council |  |  |  |  |  | 200,000.00 | 50,000.00 |  |  |  | Cent. Admin. |  |
| 176 | Sensitize Staff and Assembly Members on NACAP | Assembly Hall |  |  |  |  |  |  | 10,000.00 |  |  |  | Cent. Admin. | HR & NCCE |
| 177 | Sensitize all Town Council Members on anti-corruption and NACAP | Municipal wide |  |  |  |  |  |  | 5,000.00 |  |  |  | Cent. Admin. | NCCE, ISD |
| 178 | Organise Public forum on NACAP for religious leaders | Municipal wide |  |  |  |  |  |  | 10,000.00 |  |  |  | Cent. Admin. | NCCE, ISD |
| 179 | Develop Customer Service Charter for MA | Obuasi East Municipal Assembly |  |  |  |  |  |  | 5,000.00 |  |  |  | Cent. Admin. |  |
| 180 | Introduce measures to control absenteeism and lateness | Municipal wide |  |  |  |  |  |  | 3,000.00 |  |  |  | Cent. Admin. |  |
|  | Objective: To reduce the crime situation by 40% by the end of 2029 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programme: Security Improvement Programme |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 181 | Support to security services | Municipal wide |  |  |  |  |  |  | 100,000.00 |  |  |  | Cent. Admin. |  |

Source: OEMA- MPCU, Aug. 2025